## Sheet1
Week | Task | start date | end date | duration
Week 1 | Project Setup and Planning | 2024-11-29 | 2024-12-03 | 5
Week 2 | Data Collection and Initial Preprocessing | 2024-12-03 | 2024-12-06 | 4
Week 3 | Model Development - Text Classification | 2024-12-06 | 2024-12-10 | 5
Week 4 | Model Development - Image Classification | 2024-12-10 | 2024-12-13 | 5
Week 5 | Integration of Text and Image Models | 2024-12-13 | 2024-12-20 | 5
Week 6 | Deployment and Testing | 2024-12-31 | 2025-01-07 | 5
Week 7 | Full-Stack development | 2025-01-07 | 2025-01-10 | 5
Week 8 | Full-Stack with AWS | 2025-01-10 | 2025-01-14 | 5